Timing Plan

High-Level Overview

Phase One (Months 1–3): Identifying and Curating Research Questions Across 26 Fields

- Gather abstracts and metadata from OpenAlex.

- Use a low-parameter Large Language Model to generate questions for each abstract.

##### Complete preliminary IRB/ARB requirements.

Phase Two (Months 4–6): Model Selection and Baseline Evaluations

- Finalize the choice of LLMs for evaluation.

- Conduct initial retrieval-augmented tests and grade results.

- Refine rubrics for accuracy, analysis depth, coherence, and adaptability.

Phase Three (Months 7–9): Detailed Statistical and Qualitative Analyses

- Perform inter-rater reliability checks, ANOVA, and confidence intervals.

- Gather expert feedback in at least three specialized domains.

- Compare the strengths/weaknesses of each LLM across the 26 fields.

Phase Four (Months 10–12): Write-Up, Dissemination, and Final Defense

- Draft final dissertation chapters and incorporate feedback.

- Prepare final presentation/defense materials.

- Submit final dissertation to Chair and Committee.

## Detailed Timeline (By Weeks and Key Milestones)

Below is a week-by-week (and sometimes month-by-month) breakdown.  The four-phase plan weaves references to common elements, such as drafting and refining chapters, IRB work, continuous literature review, check-ins with the Chair, and final submission steps.

### Weeks 1–2: Initial Setup and ARB/IRB

Tasks

- Confirm ARB approval (or finalize any remaining details).

- Create a dissertation draft template with proper formatting.

- Begin Chapter 1: Introduction.

- Refine the Problem Statement, Purpose, and Significance (aligns with your ARB form).

Milestones

- ARB was officially approved.

Notes

- Align tasks with your initial Phase One goal of collecting domain materials.

- Redefining research questions as requested by ARB

### Weeks 3–4: Refining Chapter 1 and Curating Abstracts

Tasks

- Incorporate the Chair’s feedback on Chapter 1 (background, problem statement, and significance).

- Conduct a comprehensive literature search for the 26 fields.

- Begin curating abstracts from OpenAlex, focusing on ensuring domain coverage.

- Collaborate with the Chair weekly to confirm readiness for IRB submission.

Milestones

- Chapter 1 updated draft.

- The initial set of curated abstracts across at least half of the fields.

### Weeks 5–6: Finalizing IRB and Starting Chapter 2 (Literature Review)

Tasks

- Complete IRB submission and incorporate any final suggestions from the Chair.

- Begin Chapter 2: Literature Review, synthesizing domain-specific knowledge from all 26 fields.

- Identify potential “challenging” fields where subject-matter expert feedback will be crucial.

- Draft or refine your conceptual framework sections (accuracy, coherence, adaptability, domain knowledge).

Milestones

- IRB submitted.

- Chapter 2 outline (themes, subheadings for each domain) created.

### Weeks 7–8: Gathering and Annotating Domain Knowledge

Tasks

- Analyze each curated abstract systematically; produce at least one question per abstract via the low-parameter LLM (Phase One core activity).

- Begin writing key sections of Chapter 2 with a deeper focus on domain knowledge.

- Continue meeting with the Chair for feedback.

Milestones

- Completed a set of domain-specific questions in multiple fields.

- Draft segments in Chapter 2 for each significant domain theme.

### Weeks 9–10: Transition to Phase Two — Model Selection & Baseline Testing

Tasks

- Finalize the roster of LLMs to be tested.

- Document the evaluation rubrics and pilot them in a small subset of domains.

- If IRB feedback is back, address any requested revisions.

- Start writing about your methodology (Chapter 3) to capture the planned LLM comparison approach.

Milestones

- IRB approval in hand (if revisions are needed).

- Shortlist of LLMs, rubrics, and pilot test results in 1–3 domains.

### Weeks 11–12: Conducting Baseline Evaluations

Tasks

- Evaluate LLMs with the curated domain-specific questions.

- Collect quantitative/qualitative data on correctness, depth of analysis, and clarity.

- Draft the “Methods” section fully (Chapter 3).

- Continuously refine the pilot approach based on any IRB constraints.

Milestones

- Completion of baseline scoring in a few domains.

- Chapter 3 first draft (experiment setup, data gathering plan, reliability checks).

### Weeks 13–14: Deepen Literature Review and Prepare for Statistical Analysis

Tasks

- Continue refining Chapter 2.

- Start verifying the approach to inter-rater reliability, ANOVA, and confidence interval calculations.

- Ensure data collection and annotation processes are consistent.

- Check with subject-matter experts for initial feedback in at least one domain.

Milestones

- Substantial progress in Chapter 2 so that it aligns with the newly emerging methodology.

- Defined a statistical approach for your final Phase Three analyses.

### Weeks 15–16: Wrapping Up Semester Milestones

Tasks

- If your program uses semester deliverables, please submit updated Chapters 1 and 2, plus a partial Chapter 3, to the Chair or committee.

- Revisit or finalize additional references (aiming for 50–60 total).

- Refine any IRB or logistical updates.

Milestones

- Chair's acceptance of Chapters 1–2.

- Confirmation that IRB protocols are stable and data collection is authorized.

## Months 5–6 (Weeks 17–24): Phase Two Continues — Full LLM Evaluations

### Weeks 17–20: Full-Scale Data Collection

Tasks

- Execute the final set of evaluations across all 26 fields.

- Collect detailed results (true/false/possibly true/possibly false).

- Ensure thorough data logging for later statistical analysis.

Milestones

- Dataset of LLM responses with preliminary scoring.

- Ongoing weekly Chair check-ins.

### Weeks 21–24: Finalizing Chapter 3 and Preliminary Results (Chapter 4)

Tasks

- Finalize methodology text (Chapter 3).

- Begin drafting Chapter 4, focusing on raw results.

- Prepare or conduct advanced reliability tests (Miller, 2024) to see if multiple scorers align.

Milestones

- Draft of Chapter 4 with initial results.

- Full dataset ready for statistical Phase Three.

## Months 7–9 (Weeks 25–36): Phase Three — Detailed Statistical and Qualitative Analyses

### Weeks 25–28: Statistical Analysis and Expert Feedback

Tasks

- Apply ANOVA or alternative tests to detect variation across domains.

- Calculate confidence intervals to measure inter-rater reliability.

- Solicit domain experts’ input in at least three challenging fields.

Milestones

- Preliminary findings on which models excel in each field.

- Integration of expert commentary.

### Weeks 29–32: Interpretation and Chapter 4 Refinement

Tasks

- Refine Chapter 4 with a thorough statistical breakdown.

- Link the results to your conceptual framework to start bridging into the discussion portion (Chapter 5).

- Cross-check results with prior research (Ngo et al., 2024; Cai et al., 2024).

Milestones

- Polished set of tables/figures illustrating how LLMs differ across fields.

- Preliminary discussion paragraphs are in place.

### Weeks 33–36: Drafting Chapter 5 (Findings, Recommendations)

Tasks

- Draft Chapter 5 focusing on:

  - Comparison to prior literature

  - Practical applications

  - Limitations and future research

- Incorporate advanced statistical notes.

Milestones

- Substantial draft of Chapter 5.

- Provide a clear demonstration of how your dissertation addresses the identified knowledge gap.

## Months 10–12 (Weeks 37–48): Phase Four — Write-Up, Defense, and Final Submission

### Weeks 37–40: Integrating All Chapters

Tasks

- Combine Chapters 1–5 into one cohesive document.

- Revisit definitions, assumptions, and delimitations to ensure internal consistency.

- Ensure references are correctly cited.

Milestones

- Complete dissertation draft assembled.

- Submit to the Chair for a round of revisions.

### Weeks 41–44: Revision Rounds and Committee Feedback

Tasks

- Incorporate Chair and Committee feedback.

- Make final improvements to methodology, results presentation, or references.

- Prepare IRB closure documents if applicable.

Milestones

- Committee sign-off on the near-final dissertation.

- Approval to schedule the final defense.

### Weeks 45–48: Final Defense and Submission

Tasks

- Prepare an oral defense presentation.

- Rehearse and refine slides, figures, and arguments.

- Conduct dissertation defense.

- Address any post-defense editorial changes.

Milestones

- Successful defense.

- Final submission of the dissertation to the university repository.

## Continuous Tasks (Throughout the Year)

- Weekly or Bi-Weekly Check-Ins
Maintain regular Zoom or phone calls with your Chair.

- Reference Management
Continuously update and annotate references.

- Ongoing Literature Review
Keep up with new publications or relevant sources that emerge over the year.

- Document Iteration
Routinely refine chapters, completing tasks from your weekly “To Do” checklists.

- Backup and Version Control
Maintain a safe backup of your data, drafts, and references.